**MMIW Task Force Timeline**

JANUARY

* Creating a data gathering plan in consultation with Gabe and TF
* Identify stakeholders, develop involvement plan, and conduct outreach via email
* Design IPRA Requests in consultation with Gabe and TF

FEBRUARY

* Follow-up and confirm key stakeholders
* Submit IPRA Requests
* Design surveys and community hearings in consultation with Gabe and TF
* Develop the framework for gathering MMIW cases

MARCH

* Convene key stakeholders for feedback on data gathering plan
* Test and conduct one round of survey gathering
* Begin promotion/outreach for community hearings

APRIL

* Conduct community hearings
* Begin mapping MMIW cases
* Draft literature review of reports and research on MMIW
* Second round of survey gathering

MAY

* Wrap-up community hearings
* Evaluate and analyze data (surveys, IPRA requests, and community hearings)
* Develop recommendations

JUNE

* DRAFT OF FINAL REPORT